## ProjectTeam
Name | GitHub Alias
Burcu Sevinc | sevib1
Claudia Telesca | telec1
Fabian Kammermann | kammf1
Niveadha Kanagarasa | varan2
Pascal Dittli | dittp2
Patrick Jolo | jolop1
Remy Lam | lamlr1

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Login | As a user, I want to log in with my username and password | low | 16 |  |  | not started
2 | Logout | As a user, I want to log out immediately, no matter where I am | low | 8 |  |  | not started
3 | Schedule view | As a user, I want to see all patient appointments | high | 24 |  |  | in progress
4 | display information about the patient | As a user, I want to get all necessary information about a patient | high | 16 |  |  | not started
5 | display information about diagnosis | As a user, I want to see all information about patients diagnosis | medium | 12 |  |  | not started
6 | User gets past labor results from DB | As a user, I want to see past labor results | low | 12 |  |  | not started
7 | User gets standing data of patients | As a user, I want to get important information about the patients identity | high | 10 |  |  | not started
8 | status medication preparation | As a user, I want to see if I've already prepared a set of medicaments | high | 16 |  |  | not started
9 | status medications | As a user, I want to check medication | high | 16 |  |  | not started
10 | clock for schedule view | As a user, I want to see the time on the schedule view | low | 8 |  |  | not started
11 | synchronize | As a user, I want to have an option to update data | low | 16 |  |  | not started
12 | alarm | As a user, I want to inform co-workers if a patient behaves aggressively | low | 12 |  |  | not started

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Database | testdatabase, based on the uml class diagramm, filled with exampledata | Database | lamlr1 | kammf1 | high | 12 | 10 | 8 | completed
1.2 | 1 | Schedule UI | Schedule UI | UI, Controller | telec1 | jolop1 | medium | 12 | 12 | 12 | in progress
1.3 | 1 | Java Classes skeleton | Uml to Java classes | Controller, JPA Classes | sevib1 | varan2 | high | 6 | 8 | 8 | completed
1.4 | 1 | Associations | Implementing Associations | Controller, JPA Classes | kammf1 | jolop1 | high | 6 | 6 | 4 | in progress
1.5 | 1 | Getter methods | JPA - getting methods | JPA Classes, Database | varan2 | dittp2 | low | 6 | 8 | 0 | deferred
2.1 | 2 | Getter methods | JPA - getting methods | JPA Classes, Database | varan2 | dittp2 | high | 8 |  |  | not started
2.2 | 2 | Patient display | Shows in patient overview information about patient | Database, JPA, Controller,UI | dittp2 | varan2 | high | 12 |  |  | not started
2.3 | 2 | Medication display | Shows in medication overview information about medication | Database, JPA, Controller,UI | lamlr1 | jolop1 | high | 12 |  |  | not started
2.4 | 2 | Disgnosis display | Shows in disgnosis overview information about disgnosis | Database, JPA, Controller,UI | jolop1 | telec1 | medium | 12 |  |  | not started
2.5 | 2 | laboraty display | Shows in laboraty overview information about laboraty | Database, JPA, Controller,UI | kammf1 | dittp2 | medium | 12 |  |  | not started
2.6 | 2 | schedule view | Shows in schedule overview information about schedule | Database, JPA, Controller,UI | sevib1 | lamlr1 | high | 24 |  |  | in progress
80

## BurndownChart
Sprint | Week | Remaining Effort | Remaining Resources
1 | 48 | 210 | 210 | 42
1 | 49 | 178 | 168
2 | 50 |  | 126
2 | 51 |  | 84
3 | 2 |  | 42
3 | 3 |  | 0
| 4 | 0

## excel_data
status | priority
not started | low
in progress | medium
completed | high
waiting on someone else
deferred
cancelled